International Charter
Space and Major Disasters

Charter Activation	642
Charter Call ID	740
Disaster Event	Flash Flood, Landslide
Disaster Location	BRAZIL
Date of Final Reporting	27-Feb-2020

PM Report

*Reporting forms completed by: Lucas Mikosz

*Reporting forms reviewed by:

Project Managers for Charter activations are expected to provide the PM report to the Charter Executive Secretariat within 45 days after the start of the activation.

A. Disaster Event Summary
*A1. Disaster type:	Flash Flood, Landslide
*A2. Date disaster started: 17-Jan-2020
*A3. Disaster location and extent: BRAZIL
A4. Estimated number of deaths: 10
A5. Estimated number of people affected: 15000
A6. Estimated economic losses:
A7. Additional impacts of disaster (environmental, infrastructure, etc): At least 40 bridges destroyed. Damages to agriculture estimated at BRL 88 millions.
A8. Additional disaster event details: In the State of Espirito Santo only, 40 municipalities were affected and from those, 22 cities declared state of emergency or calamity.

* mandatory

B. Affected Areas

Area of Interest ID	Priority	AoI Name	Comments	KML
Call-740 ID: 1	1	POI-01 - Iconha	Radius (km): 3; Heavy cloud cover expected for next days	download

C.People Involved
*C1a. Authorized User/Requestor: Lucas Mikosz	*C1b. Organization: CENAD	*C1c. Date AU/CB requested activation: 24-Jan-2020 01:08:00
Identify the agency if any that requested the Charter activation:
*C3a. ECO: ECO_JAXA ECO_JAXA	*C3b. Organization:	*C3c. Date of Dossier generation: 24-Jan-2020 02:36:44
*C4a. Project Manager: Lucas Mikosz	*C4b. Organization: INPE	*C4c. Date of PM nomination: 24-Jan-2020 09:11:43 by INPE

* mandatory

D. Product List
Agency	Satellite / Instrument / Mode	Satellite Sensing date	Date PM received image	Archive	Useful Products
KARI	KOMPSAT5 / COSI / Standard	10-Sep-2019	29-Jan-2020	Yes	-
KARI	KOMPSAT3A / AEISS / PMS	12-Sep-2019	29-Jan-2020	Yes	-
USGS	WORLDVIEW_3 / EO_IMAGER	21-Sep-2019	27-Jan-2020	Yes	-
USGS	WORLDVIEW_3 / EO_IMAGER	21-Sep-2019	27-Jan-2020	Yes	-
USGS	WORLDVIEW_3 / EO_IMAGER	21-Sep-2019	27-Jan-2020	Yes	-
CSA	RADARSAT2 / SAR_RAD_2 / WIDE_FINE	16-Dec-2019	29-Jan-2020	Yes	-
CSA	RADARSAT2 / SAR_RAD_2 / WIDE_FINE	09-Jan-2020	29-Jan-2020	Yes	-
ESA	SENTINEL_1B / SAR_ESA / IWS	19-Jan-2020	24-Jan-2020	No	-
ESA	SENTINEL_1B / SAR_ESA / IWS	19-Jan-2020	24-Jan-2020	No	-
ESA	SENTINEL_1A / SAR_ESA / IWS	24-Jan-2020	25-Jan-2020	No	-
ESA	SENTINEL_1A / SAR_ESA / IWS	24-Jan-2020	25-Jan-2020	No	-
ESA	SENTINEL_1A / SAR_ESA / IWS	25-Jan-2020	25-Jan-2020	No	First useful crisis (post-event) image
ESA	SENTINEL_1A / SAR_ESA / IWS	25-Jan-2020	25-Jan-2020	No	Second useful crisis (pre-event) image
DLR	TANDEM_X / SAR / SpotLight	25-Jan-2020	26-Jan-2020	No	-
ESA	SENTINEL_1B / SAR_ESA / IWS	25-Jan-2020	26-Jan-2020	No	-
CSA	RADARSAT2 / SAR_RAD_2 / ULTRA_FINE	26-Jan-2020	29-Jan-2020	No	-
KARI	KOMPSAT5 / COSI / High Resolution	28-Jan-2020	29-Jan-2020	No	-
CSA	RADARSAT2 / SAR_RAD_2 / ULTRA_FINE	28-Jan-2020	29-Jan-2020	No	-
KARI	KOMPSAT5 / COSI / Standard	29-Jan-2020	31-Jan-2020	No	-
KARI	KOMPSAT5 / COSI / High Resolution	30-Jan-2020	31-Jan-2020	No	-
KARI	KOMPSAT3 / AEISS / PMS	30-Jan-2020	31-Jan-2020	No	-
ESA	SENTINEL_1B / SAR_ESA / IWS	30-Jan-2020	31-Jan-2020	No	-
ESA	SENTINEL_1B / SAR_ESA / IWS	31-Jan-2020	02-Feb-2020	No	-
ESA	SENTINEL_1A / SAR_ESA / IWS	31-Jan-2020	01-Feb-2020	No	-
ESA	SENTINEL_1A / SAR_ESA / IWS	31-Jan-2020	01-Feb-2020	No	-
USGS	WORLDVIEW_2 / EO_IMAGER	02-Feb-2020	03-Feb-2020	No	-
USGS	LANDSAT8 / OLI_TIRS	04-Feb-2020	05-Feb-2020	No	-

E. Chronology of Events
Date	Call ID	Performed by	Action
24-Jan-2020 01:08:33	740	AU_BR_CENAD	AU call submission
24-Jan-2020 01:08:33	740	AU_BR_CENAD	Call 740:
24-Jan-2020 01:23:19	740	ODO	ODO confirmation, ECO call notification
24-Jan-2020 02:03:20	740	ECO_JAXA	ECO URF validation
24-Jan-2020 02:33:06	740	ECO_JAXA	ERF v.1 sent to MPP of CNES
24-Jan-2020 02:33:08	740	ECO_JAXA	ERF v.1 sent to MPP of CNSA
24-Jan-2020 02:33:09	740	ECO_JAXA	ERF v.1 sent to MPP of CSA
24-Jan-2020 02:33:10	740	ECO_JAXA	ERF v.1 sent to MPP of DLR
24-Jan-2020 02:33:12	740	ECO_JAXA	ERF v.1 sent to MPP of ESA
24-Jan-2020 02:33:13	740	ECO_JAXA	ERF v.1 sent to MPP of ISRO
24-Jan-2020 02:33:14	740	ECO_JAXA	ERF v.1 sent to MPP of JAXA
24-Jan-2020 02:33:15	740	ECO_JAXA	ERF v.1 sent to MPP of KARI
24-Jan-2020 02:33:16	740	ECO_JAXA	ERF v.1 sent to MPP of MBRSC
24-Jan-2020 02:33:17	740	ECO_JAXA	ERF v.1 sent to MPP of PLANET
24-Jan-2020 02:33:19	740	ECO_JAXA	ERF v.1 sent to MPP of ROSCOSMOS
24-Jan-2020 02:33:20	740	ECO_JAXA	ERF v.1 sent to MPP of USGS
24-Jan-2020 02:36:44	740	ECO_JAXA	ECO Dossier completed
24-Jan-2020 05:35:40	740	MPP_ROSCOSMOS	AAP received from MPP of ROSCOSMOS
24-Jan-2020 06:45:20	740	MPP_DLR	AAP received from MPP of DLR
24-Jan-2020 08:54:33	740	MPP_ESA	AAP received from MPP of ESA
24-Jan-2020 09:11:43	740	ES_INPE_LNamikawa	PM nominated by INPE
24-Jan-2020 11:38:47	740	PM_INPE_LMikosz	ECO Dossier validated by PM
24-Jan-2020 13:30:52	740	test	Data Product received from MPP of ESA
24-Jan-2020 13:31:01	740	test	Data Product received from MPP of ESA
24-Jan-2020 19:23:05	740	MPP_CSA	AAP received from MPP of CSA
25-Jan-2020 00:30:28	740	test	Data Product received from MPP of ESA
25-Jan-2020 00:30:37	740	test	Data Product received from MPP of ESA
25-Jan-2020 12:30:30	740	test	Data Product received from MPP of ESA
25-Jan-2020 12:30:37	740	test	Data Product received from MPP of ESA
26-Jan-2020 00:00:44	740	test	Data Product received from MPP of ESA
26-Jan-2020 03:16:37	740	MPP_DLR	Data Product received from MPP of DLR
26-Jan-2020 23:43:27	740	PM_INPE_LMikosz	VAP uploaded
27-Jan-2020 13:00:20	740	MPP_USGS	Data Product received from MPP of USGS
27-Jan-2020 13:00:32	740	MPP_USGS	Data Product received from MPP of USGS
27-Jan-2020 13:00:44	740	MPP_USGS	Data Product received from MPP of USGS
28-Jan-2020 05:32:28	740	MPP_KARI	AAP received from MPP of KARI
28-Jan-2020 05:50:54	740	MPP_KARI	AAP received from MPP of KARI
28-Jan-2020 05:54:03	740	MPP_KARI	AAP received from MPP of KARI
28-Jan-2020 23:22:29	740	PM_INPE_LMikosz	VAP uploaded
29-Jan-2020 02:05:35	740	MPP_KARI	Data Product received from MPP of KARI
29-Jan-2020 02:06:51	740	MPP_KARI	Data Product received from MPP of KARI
29-Jan-2020 04:33:56	740	MPP_KARI	Data Product received from MPP of KARI
31-Jan-2020 07:12:31	740	MPP_KARI	Data Product received from MPP of KARI
31-Jan-2020 08:10:06	740	MPP_KARI	Data Product received from MPP of KARI
31-Jan-2020 08:12:11	740	MPP_KARI	Data Product received from MPP of KARI
31-Jan-2020 11:00:45	740	test	Data Product received from MPP of ESA
01-Feb-2020 17:00:38	740	test	Data Product received from MPP of ESA
01-Feb-2020 17:00:42	740	test	Data Product received from MPP of ESA
01-Feb-2020 21:00:06	740	PM_INPE_LMikosz	VAP uploaded
02-Feb-2020 02:30:31	740	test	Data Product received from MPP of ESA
03-Feb-2020 13:06:42	740	MPP_USGS	Data Product received from MPP of USGS
05-Feb-2020 14:18:37	740	MPP_USGS	Data Product received from MPP of USGS

F. Value Added Product List
*F1a. Sending date to requestor of the first Value-adding products (e.g. maps and charts from the PM or VAR) based on archive images: null UTC
*F1b. Sending date to requestor of the first Value-adding crisis product (can be a product based on both archive and crisis images): 27-Jan-2020 08:00 UTC
*F1c. The date the first VA crisis product was provided: 26-Jan-2020 23:34 UTC
*F2. Available value added product data list
Title	Source(s)	Acquistion dates
Destroyed Bridges in Iconha/ES	PLEIADES_1B	01-Feb-2020 07:40:02
Floods in Espirito Santo State	RADARSAT2 SENTINEL_1A TERRASAR_X LANDSAT8	26-Jan-2020 06:00:45 25-Jan-2020 08:13:19 25-Jan-2020 06:00:52 31-Oct-2019 06:00:15
Floods in Brazil - Espirito Santo State - Itapemirim area	SENTINEL_1A	25-Jan-2020 08:13:48

* mandatory

G. Activation Assessment

G1. PM User assessment - usefulness of data provided by the Charter.

*G1.1 Did the post-disaster data ordered by the ECO (prescribed data) meet your expectations?

Service		Greatly exceeded expectations	Exceeded Expectations	Matched Expectations	Less than Expected	Much Less than Expected	Not Applicable
a. Range/type of data (optical, radar)			X
b. Number of products provided (type, quantity, volume of data)			X
c. Coverage (visibility of area of interest)			X
d. Usefulness of radar data		X
e. Usefulness of optical data with a resolution higher than 2 m				X
f. Usefulness of optical data with a resolution lower than 2 m			X
g. Timeliness of data delivery			X

*G1.2 Did the pre-disaster data ordered by the ECO (prescribed data) meet your expectations?

Service		Greatly exceeded expectations	Exceeded Expectations	Matched Expectations	Less than Expected	Much Less than Expected	Not Applicable
a. Range/type of data (optical, radar)				X
b. Number of products provided (type, quantity, volume of data)				X
c. Coverage (visibility of area of interest)				X
d. Usefulness of radar data			X
e. Usefulness of optical data with a resolution higher than 2 m				X
f. Usefulness of optical data with a resolution lower than 2 m				X
g. Timeliness of data delivery			X

*G1.3 If you requested additional Charter data, did these data meet your expectations?

Service		Greatly exceeded expectations	Exceeded Expectations	Matched Expectations	Less than Expected	Much Less than Expected	Not Applicable
a. Range/type of data (optical, radar)							X
b. Number of products provided (type, quantity, volume of data)							X
c. Coverage (visibility of area of interest)							X
d. Usefulness of radar data							X
e. Usefulness of optical data with a resolution higher than 2 m							X
f. Usefulness of optical data with a resolution lower than 2 m							X
g. Timeliness of data delivery							X

G1.4 If you were not fully satisfied with the Charter data, please provide further details:

G1.5 Did you use satellite data from outside the Charter to support this event? If so, please indicate the type and their source

G2. Usefulness of value adding service provided through the Charter

*G2.1 List the value-added products obtained from the Charter data:

a. Shape files	_
b. Image files	X
c. Web mapping services	_
d. Others, please state

*G2.2 How useful do you think the value-added products were for the end user(s)?

a. Very useful	_
b. Partially useful	X
c. Not so useful	_
d. Unknown	_

G2.3 If you believe the value-added products were not so useful, please explain why:

G2.4 How could the value added products be improved to make them more useful for the end user(s)?

Poor communication between the field response team and the central government emergency mapping team delayed the field needs assessment

G3. Assessment of overall Charter process in support of this call

*G3.1 Did the following steps in the Charter process meet with your expectations? (Indicate your level of satisfaction by placing an [X] in the appropriate box):

Service		Greatly exceeded expectations	Exceeded Expectations	Matched Expectations	Less than Expected	Much Less than Expected	Not Applicable
a. Assignment of PM (e.g. role acknowledgement, PM Welcome Package)			X
b. Communication with the ECO (e.g. Delivery of ECO Dossier)		X
c. Interface between the PM and Order Desks (if applicable)			X
d. Performing licensing / signature of NDAs				X
e. Interface between the PM and the End User(s)							X
f. Interface between the PM and ES		X
g. Interface between the PM and VA							X
h. Use of the COS-2 system			X

*G3.2 If you had to accept licensing terms and conditions / sign Non-Disclosure Agreements during this Charter call, did the procedure run smoothly?

a. Yes	X
b. No	_
c. Not applicable	_

If you experienced problems during the process, please provide further details:

G3.3 If you were not satisfied with any step in the Charter process, please let us know why:

G4. How could we improve the service to better support Project Managers?

In this call the End Users, PM and VAs came from the same institution (CENAD - National Center of Risk and Disaster Management - Brazil).

H. Supporting Documentation
*H1. Provide samples of media coverage of the disaster event from TV, radio, newspapers, websites, etc. Where possible, copy the content of the article into the PM report rather than only the web addresses: / Available at / https://www.theguardian.com/world/2020/jan/27/heavy-rain-landslides-flooding-mass-evacuations-brazil / ------ / Headline translation: Number of deaths by the rains at ES reaches 10, after missing body found. / Available at: / https://g1.globo.com/es/espirito-santo/noticia/2020/01/30/sobe-para-10-o-no-de-mortos-por-causa-das-chuvas-no-es-apos-corpo-de-desaparecida-ser-encontrado.ghtml / --- / Headline translation: Rain causes deaths, isolate cities and causes damages on ES. / https://www.agazeta.com.br/es/sul/chuva-deixa-mortos-isola-cidades-e-gera-prejuizo-no-es-veja-ponto-a-ponto-0120
*H2. Most relevant value-added products
VAP title: Destroyed Bridges in Iconha/ES VAP creation date: 01-Feb-2020
VAP title: Floods in Espirito Santo State VAP creation date: 28-Jan-2020
VAP title: Floods in Brazil - Espirito Santo State - Itapemirim area VAP creation date: 26-Jan-2020

* mandatory

I. End User Feedback

Attach a copy of user feedback forms (Annex G) submitted by the end users or email correspondence regarding the end user(s).

I1. Describe the activation in detail and describe the interaction between the PM and the AU:

In this activation, both the PM and AU belong to CENAD - National Center of Risk and Disaster Management in Brazil. The activation of the charter was requested by the director of CENAD, after he arrived at the area with the damage assessment team and realized it was difficult to assess the size of the disaster, as many bridges collapsed and some communities were isolated. As the cloud cover remained high during most of the activation, the Radar products were used to understand the real extent of the floods, during the initial stages of the activation.

International Charter
Space and Major Disasters

End User Feedback Report

End User	Lucas Mikosz
Organization
Charter Call ID #	740
Disaster Event	Flash Flood, Landslide
Disaster Location	BRAZIL

Activating of the Charter:

Did you encounter difficulties in triggering the Charter?					_ Yes	X No
Did you use COS-2 to activate the Charter?					X Yes	_ No
If you used COS-2 to activate the Charter, did you find it easy to use?					X Yes	_ No

How could we make the activation process better for you?

The current procedure is working perfectly

Provision of Charter Data and Value-added Products:

Did you receive original satellite data in addition to value-added products?					X Yes	_ No

B2 Rate how well the following aspects of the data and/or value-added products matched with your expectations:

	Data / Value Added Product	Greatly exceeded expectations	Exceeded Expectations	Matched Expectations	Less than Expected	Much Less than Expected	Not Applicable
a.	Range/type of data (optical, radar)		X
b.	Number of products provided (type, quantity, volume of data)		X
c.	Coverage (visibility of area of interest)			X
d.	Usefulness of Radar data	X
e.	Usefulness of optical data with a resolution higher than 2 m		X
f.	Usefulness of optical data with a resolution lower than 2 m			X
g.	Timeliness of delivery	X
h.	Format	X

Did you use satellite data and/or value-added products from outside the Charter to support this event? If so, please indicate the type and their source:

No

How were the data and/or value-added products used?

Operations	X
Communication	X
Planning	_
Documentation	X
Lessons Learned / Training	_
Other	_
Not used	_

How could the data and/or value-added products be improved to make them more useful?

Slow communication between the field and emergency mapping teams delayed the understanding of what kind of information would be useful for the field operations.

Working with the Charter:

How would you rate the communication between the end user(s) and the Project Manager during this call?

Greatly exceeded expectations	_
Exceeded Expectations	_
Matched Expectations	X
Less than Expected	_
Much Less than Expected	_

How would you rate the contribution made by the Charter to this emergency?

Greatly exceeded expectations	_
Exceeded Expectations	X
Matched Expectations	_
Less than Expected	_
Much Less than Expected	_